## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product
B | Develop marketing strategy
C | Design brochure | A
D | Develop product prototype
D1 | Requirements analysis | A
D2 | Software design | D1
D3 | System design | D1
D4 | Coding | D2, D3
D5 | Write documentation | D4
D6 | Unit testing | D4
D7 | System testing | D6
D8 | Package deliverables | D5, D7
E | Survey potential market | B, C
F | Develop pricing plan | D8, E
G | Develop implementation plan | A, D8
H | Write client proposal | F, G

## Sheet2
Task ID | Task | Best-Case Hours | Expected Hours | Worst-Case Hours
A | Describe product | 4 | 8 | 12
B | Develop marketing strategy | 2 | 6 | 10
C | Design brochure | 6 | 10 | 16
(Predecessor: A)
D | Develop product prototype | ∗AggregatesD1–D8∗*Aggregates D1–D8*∗AggregatesD1–D8∗ | ∗Aggregates∗*Aggregates*∗Aggregates∗ | ∗Aggregates∗*Aggregates*∗Aggregates∗
D1 | Requirements analysis | 6 | 10 | 15
(Predecessor: A)
D2 | Software design | 8 | 12 | 18
(Predecessor: D1)
D3 | System design | 8 | 12 | 18
(Predecessor: D1)
D4 | Coding | 16 | 24 | 40
(Predecessor: D2, D3)
D5 | Write documentation | 4 | 8 | 12
(Predecessor: D4)
D6 | Unit testing | 6 | 10 | 15
(Predecessor: D4)
D7 | System testing | 8 | 12 | 20
(Predecessor: D6)
D8 | Package deliverables | 4 | 8 | 12
(Predecessor: D5, D7)
E | Survey potential market | 6 | 12 | 18
(Predecessor: B, C)
F | Develop pricing plan | 4 | 8 | 12
(Predecessor: D8, E)
G | Develop implementation plan | 4 | 8 | 12
(Predecessor: A, D8)
H | Write client proposal | 4 | 8 | 12
(Predecessor: F, G)

## Sheet3
Project Manager: $70/hour
Frontend Developer: $60/hour
Backend Developer: $65/hour
Data Scientist: $80/hour
Data Engineer: $75/hour